## Roadmap Overview
STRATOSDB 6-MONTH ENGINEERING ROADMAP (POSTGRESQL & MYSQL PARITY PROGRAM)
Executive Architecture & Strategic Timeline: From Advanced Prototype to Production-Grade RDBMS
Month | Timeline | Primary Phase Focus | Key Architectural Deliverables | Target Performance / Quality Gate
Month 1 | Weeks 01 - 04 | Storage & Durability Hardening | Compact schema-less Tuple encoding, WAL redo for B-Tree splits/merges, Free Space Map (FSM), Page LSNs | Zero data loss under SIGKILL, 75% disk space reduction
Month 2 | Weeks 05 - 08 | Relational Catalog & Constraints Engine | Transaction catalog tables (replacing catalog.txt), Enforced PK, UNIQUE, FOREIGN KEY (CASCADE), CHECK, NOT NULL | 100% schema integrity, full pg_catalog / information_schema emulation
Month 3 | Weeks 09 - 12 | Volcano Iterator Execution Engine | Streaming pipeline: PhysicalOperator (open, next, close), Left/Right/Full Outer Joins, subquery unnesting | O(1) memory per query pipeline, no OOM on 10M row table scans
Month 4 | Weeks 13 - 16 | Cost-Based Optimizer & Concurrency | HyperLogLog statistics, Histograms, MCV lists, Join reordering (DP), B+Tree multi-page latch crabbing | 10x speedup on complex multi-join queries, zero race conditions under 64 concurrent threads
Month 5 | Weeks 17 - 20 | Protocol Completeness & Enterprise Security | Binary parameter decoding in pgwire, native SSL/TLS encryption in StdWireServer, SCRAM-SHA-256-PLUS | Full psql, DBeaver, DataGrip, Prisma, Hibernate ORM compatibility
Month 6 | Weeks 21 - 26 | High Availability, Benchmarking & Launch | Distributed consensus failover (Raft/etcd), networked base backups, TPC-C/Sysbench suites, ZGC tuning | >25,000 QPS on TPC-B/TPC-C, sub-millisecond P99 latency
STRATEGIC CORE OBJECTIVES
1. Durability First | All heap, index, and catalog mutations must be fully covered by physiological WAL logging with Page LSN idempotency.
2. Streaming Pipelining | Eliminate all monolithic in-memory ArrayList<Tuple> collections in ExecutorEngine; switch to Volcano Iterator model.
3. Production Compatibility | Speak Postgres v3 wire protocol and catalog queries so transparently that standard clients cannot tell StratosDB apart from native Postgres.
4. Predictable Zero-Pause Latency | Employ off-heap byte buffers, direct memory allocation, and Generational ZGC to ensure zero Stop-The-World GC latency spikes.

## 26-Week Sprint Plan
STRATOSDB 26-WEEK DETAILED SPRINT BACKLOG
Detailed Task-by-Task Engineering Breakdown Across 13 Two-Week Sprints
Sprint | Week | Phase / Area | Technical Task Name | Detailed Engineering Scope | Complexity | Priority | Definition of Done (DoD) & Verification | Status
Sprint 1 | Week 01 | Storage Engine | Schema-less Binary Tuple Serialization | Refactor Tuple.java and SlottedPage to remove columnNames from row bytes. Row format: [Header (xmin, xmax, infomask, null_bitmap) ¦ Var-len offset table ¦ Column values]. Schema is resolved dynamically against the catalog. | High | Critical | Tuples store raw bytes only; 75%+ reduction in row size; existing crash tests pass. | Completed
Sprint 1 | Week 02 | Storage Engine | Free Space Map (FSM) & Page LSNs | Implement 2-level Free Space Map (FSM) tracking available bytes per page. Add 8-byte PageLSN to SlottedPage header. HeapTable.insert() queries FSM in O(1) instead of scanning every page. | Medium | Critical | HeapTable.insert() reaches O(1) page lookup amortized; PageLSN checked during redo. | Completed
Sprint 2 | Week 03 | Storage / WAL | B+Tree WAL Logging & Redo | Add WAL records for index mutations: OP_INDEX_INSERT, OP_INDEX_SPLIT, OP_INDEX_DELETE, OP_INDEX_MERGE. Replay index operations during WALManager.recover(). | High | Critical | SIGKILL during B+tree leaf split recovers with zero orphan pointers or broken links. | Completed
Sprint 2 | Week 04 | Storage / Memory | Direct Memory Buffer Pool & Off-Heap Storage | Migrate BufferPool from byte[] heap arrays to DirectByteBuffer / Java 25 Foreign MemorySegment. Eliminate GC overhead on page caches. Add Dirty Page background flush thread. | High | High | Page data stored completely off-heap; GC heap allocation drops to near zero during sequential scans. | Completed
Sprint 3 | Week 05 | Catalog System | Transactional Relational System Catalog | Retire catalog.txt. Create internal system tables: stratos_tables, stratos_columns, stratos_indexes, stratos_types, stratos_constraints. DDL executes as transactional ACID writes. | High | Critical | CREATE/ALTER/DROP TABLE updates system tables; rollback in transaction rolls back schema changes. | Completed
Sprint 3 | Week 06 | Catalog / Wire | std_catalog & information_schema Emulation | Implement virtual/system views for std_class (pg_class), std_attribute (pg_attribute), std_type, std_namespace, std_index, and information_schema.tables. Wire them into query engine. | Medium | High | stdsql commands \d, \dt, \l, and tab-completion work seamlessly out of the box. | Completed
Sprint 4 | Week 07 | Constraint Engine | Primary Key & Unique Constraint Enforcement | Enforce PRIMARY KEY and UNIQUE constraints via backing unique B+Tree index. Reject duplicate insertions on INSERT and UPDATE statements with standard SQLSTATE 23505. | Medium | Critical | Duplicate key inserts throw UniqueConstraintViolationException; verified in concurrent tests. | Completed
Sprint 4 | Week 08 | Constraint Engine | Foreign Key Referential Integrity Engine | Implement REFERENCES clause parsing and runtime enforcement. Support ON DELETE CASCADE, ON DELETE RESTRICT, ON DELETE SET NULL, and ON UPDATE CASCADE. Enforce NOT NULL and CHECK expressions. | High | Critical | Orphan inserts blocked; cascading deletes remove child rows atomically in the same transaction. | Completed
Sprint 5 | Week 09 | Query Execution | Volcano Iterator Framework (Physical Operators) | Define PhysicalOperator interface: open(), next(): TupleSlot, close(). Implement SeqScanOperator, IndexScanOperator, FilterOperator, ProjectOperator, LimitOperator. Stream rows one by one. | High | Critical | Queries stream rows without accumulating List<Tuple> in memory; memory footprint remains constant. | Planned
Sprint 5 | Week 10 | Query Execution | Streaming Join Operators | Build NestedLoopJoinOperator, HashJoinOperator (in-memory hash table on build side, streaming probe), and MergeJoinOperator (presorted streaming merge). Add LEFT/RIGHT/FULL OUTER JOINs. | High | High | Outer joins pass SQL conformance tests; memory scales only with build table size. | Planned
Sprint 6 | Week 11 | Query Execution | Streaming Sort & Aggregation | Implement SortOperator (in-memory QuickSort with spill-to-disk external merge sort for >work_mem) and HashAggregateOperator / StreamAggregateOperator for GROUP BY and HAVING. | High | High | GROUP BY combined with JOINs works cleanly; 1M row ORDER BY does not trigger OutOfMemoryError. | Planned
Sprint 6 | Week 12 | Query Engine | Subquery Unnesting & Decorrelation | Rewrite correlated IN, EXISTS, and scalar subqueries into semi-joins and anti-joins during AST planning phase. Enable subqueries in FROM clause and JOIN targets. | High | Medium | Correlated subqueries achieve 50x-100x speedup by converting from O(N*M) nested loops to Hash Joins. | Planned
Sprint 7 | Week 13 | Index Subsystem | B+Tree Multi-Page Latch Crabbing (Coupling) | Implement latch crabbing in BTreeIndex: acquire read latch on child before releasing parent; acquire write latches down to leaf on split/merge. Ensure zero deadlocks between concurrent readers and writers. | High | Critical | 64 threads running concurrent inserts and range scans for 10 minutes with zero corruption or deadlocks. | Planned
Sprint 7 | Week 14 | Index Subsystem | Free-Page Management & Index Defragmentation | Implement freelist for BTreeIndex pages when nodes merge. Reclaim orphaned pages for future splits instead of endlessly growing index files. Add REINDEX TABLE support. | Medium | Medium | Index file size stabilizes under continuous insert-delete churn. | Planned
Sprint 8 | Week 15 | Query Optimizer | Statistics Engine (ANALYZE 2.0) | Build persistent table statistics: row counts, page counts, null fraction, average width, HyperLogLog for distinct values, and equi-depth histograms + MCV (Most Common Values) lists. | High | High | ANALYZE generates realistic column selectivity estimates; persisted in stratos_statistic. | Planned
Sprint 8 | Week 16 | Query Optimizer | Cost-Based Optimizer & Join Reordering | Implement System-R style Dynamic Programming optimizer for multi-table join reordering. Model I/O cost (seq_page_cost=1.0, random_page_cost=4.0) and CPU cost (cpu_tuple_cost=0.01). | High | High | Planner correctly selects IndexScan vs SeqScan and optimal join order (e.g. A join B join C). | Planned
Sprint 9 | Week 17 | Wire Protocol | Native Binary Parameter Decoding | Replace text query interpolation in Extended Protocol (Bind/Execute). Parse native pgwire binary formats (int2, int4, int8, float4, float8, timestamp, bytea, text) directly into strongly typed values. | Medium | Critical | Binary parameters handled without string conversion; eliminates SQL injection surface completely. | Planned
Sprint 9 | Week 18 | Security / Network | TLS/SSL Integration in StdWireServer | Implement SSLEngine handshake in StdWireServer responding to SSLRequest packet ('S'). Support TLS 1.3, configurable keystore/truststore, ALPN, and client certificate authentication. | High | Critical | psql sslmode=require and sslmode=verify-full connect securely; traffic verified encrypted via Wireshark. | Planned
Sprint 10 | Week 19 | Transactions | Isolation Levels: Read Committed vs Repeatable Read | Support SET TRANSACTION ISOLATION LEVEL. Read Committed acquires fresh MVCC snapshot per statement; Repeatable Read preserves snapshot created at transaction begin. Add SELECT ... FOR UPDATE. | High | High | Non-repeatable reads observed under Read Committed, prevented under Repeatable Read. FOR UPDATE locks rows. | Planned
Sprint 10 | Week 20 | Security / Auth | SCRAM-SHA-256-PLUS Channel Binding & Roles | Implement RFC 5802 channel binding (tls-unique / tls-server-end-point). Add role inheritance (GRANT role TO user) and database-level permissions. | Medium | Medium | Prevents MITM attacks on TLS connections; multi-tier role hierarchies function correctly. | Planned
Sprint 11 | Week 21 | Replication & HA | Networked Base Backup Protocol | Implement pgwire BASE_BACKUP replication command. Primary streams raw tarball/pages of data directory over replication connection while active WAL is archived. Replica bootstraps automatically. | High | High | New replica bootstraps from running primary over network without manual file copying. | Planned
Sprint 11 | Week 22 | Replication & HA | Distributed Consensus Failover (Raft Watchdog) | Upgrade StratosHa watchdog with Raft consensus / etcd lease integration. Eliminate single-point-of-failure split-brain risk during network partitions. | High | High | Network partition does not cause dual primaries; automatic failover succeeds in <3 seconds. | Planned
Sprint 12 | Week 23 | Driver & Ecosystem | Full ORM & Client Ecosystem Certification | Certify StratosDB against Hibernate ORM 6.x, Spring Data JPA, Prisma ORM, DBeaver, and DataGrip. Fix dialect edge-cases (sequence syntax, metadata introspection, types). | Medium | High | Spring Boot PetClinic and Prisma demo apps run without code modifications. | Planned
Sprint 12 | Week 24 | Performance Tuning | JVM Zero-Pause Tuning & JIT Optimization | Configure Generational ZGC (-XX:+UseZGC -XX:+ZGenerational), tune buffer pool direct allocation, profile flame graphs using async-profiler. Eliminate allocation hotspots in hot paths. | Medium | High | P99 latency stays under 1.5ms under 10,000 TPS write load; zero STW pauses >2ms. | Planned
Sprint 13 | Week 25 | Benchmarking | TPC-C & Sysbench Performance Certification | Run TPC-C (50 warehouses) and Sysbench (oltp_read_write, 10M rows) against StratosDB, PostgreSQL 16, and MySQL 8.0. Publish reproducible benchmark scripts and reports. | High | High | StratosDB achieves >70% of PostgreSQL throughput on identical hardware with linear scaling. | Planned
Sprint 13 | Week 26 | Release Engineering | StratosDB 1.0 Production Release & Docker Packaging | Finalize documentation, production deployment guides, official Docker image, Kubernetes Helm chart with automated replication, and publish Maven central driver artifact. | Medium | Critical | One-click docker run stratosdb:1.0 ready; comprehensive documentation published. | Planned

## Gap Analysis vs PG and MySQL
DEEP ARCHITECTURAL GAP ANALYSIS: STRATOSDB VS. POSTGRESQL & MYSQL
Detailed Component-by-Component Subsystem Evaluation & 6-Month Target State
Subsystem | Architectural Dimension | PostgreSQL 16 | MySQL 8.0 (InnoDB) | StratosDB Current | Impact / Severity | Target State (6 Months)
Catalog | Schema Storage & Catalog Format | Relational system tables (pg_class, pg_attribute) with MVCC transactions | InnoDB transactional data dictionary (mysql.*) | Resolved (Sprint 3): Relational catalog tables (stratos_tables, stratos_columns, etc.) with transactional ACID DDL | CRITICAL | Relational catalog tables with transactional DDL
Catalog | Database & Namespace Multi-Tenancy | Clusters contain Databases; Databases contain Schemas (CREATE SCHEMA) | Catalogs contain Schemas/Databases interchangeably | Single database instance (StratosCluster handles basic multi-db) | Medium | Support CREATE SCHEMA and search_path resolution
Catalog | System Views / Tooling Inspection | Extensive pg_catalog views and information_schema standards | information_schema and performance_schema tables | Resolved (Sprint 3): Emulated std_catalog (std_class, std_attribute, etc.) & information_schema for stdsql & GUI tooling | High | Emulated std_catalog enabling stdsql, DBeaver, DataGrip
Storage | Page Format & Slot Header | Slotted Page (8KB), ItemPointer table, HeapTupleHeaderData (xmin, xmax, ctid) | Clustered Index B+Tree (16KB), Record header, Roll pointer, DB_TRX_ID | Resolved (Sprint 1): Standard Slotted Page with 8-byte PageLSN header (pd_lsn) and dirty tracking; checked during redo. | Resolved | Standard Slotted Page with Page LSN and dirty bit
Storage | Tuple Serialization Layout | Schema-less: header + null bitmap + raw contiguous column values. No names. | Compact binary format: null bitmap + var-len offsets + column data. | Resolved (Sprint 1): Schema-less binary tuple layout with null bitmap & var-len offset table (-75%+ size reduction) | Resolved | Remove column names; compact raw byte tuple format (-75% size)
Storage | Large Value Handling (TOAST / LOB) | TOAST tables: transparent compression + out-of-line page chunking (>2KB) | Off-page overflow pages for VARCHAR/TEXT/BLOB > 768 bytes | None: row size cannot exceed single page (fails on >8KB rows) | Medium | TOAST-style overflow pages for TEXT and BYTEA
Storage | Page Space Allocation & Discovery | Free Space Map (FSM) 2-level tree for O(1) space lookup | Extent descriptors and Free page lists in file space header | Resolved (Sprint 1): Two-level Free Space Map (FSM) with Level 1 leaf chunks and Level 2 summary array; O(1) amortized page discovery. | Resolved | Two-level Free Space Map (FSM) for O(1) page discovery
Transactions | MVCC Mechanism | Append-only multi-version tuples in heap; vacuum cleans dead versions | In-place updates in clustered index; old versions stored in Undo Log chains | Append-only tuple versions in heap; vacuum defragments slots | Medium | Retain Postgres-style MVCC; vacuum horizon safety
Transactions | Transaction Isolation Levels | Read Committed (snapshot per query), Repeatable Read, Serializable (SSI) | Read Uncommitted, Read Committed, Repeatable Read (Gap Locks), Serializable | Snapshot Isolation fixed at transaction start | High | Differentiate Read Committed vs Repeatable Read + FOR UPDATE
Transactions | Row Locking & Concurrency Control | Row lock flags in tuple header (infomask), heavy locks in LockManager | Record locks, Gap locks, Next-Key locks in InnoDB lock sys | LockManager with wait-for graph deadlock detection; HeapTable page latches | High | Add explicit SELECT FOR UPDATE and row-level lock tracking
WAL / Durability | Recovery Algorithm | ARIES recovery: Analysis, Redo (from checkpoint RedoRecPtr), Undo (via MVCC) | ARIES recovery: Redo log replay + Undo rollback of uncommitted trx | Two-pass Redo log scan; uncommitted writes hidden by MVCC | Medium | Physiological Redo with Page LSN check
WAL / Durability | Index WAL Logging | All B-Tree, GIN, GiST, BRIN page splits and merges are WAL logged | All index page mutations are logged in InnoDB redo log | Resolved (Sprint 2): B+Tree index mutations (INSERT, SPLIT, DELETE, MERGE) are fully WAL logged and replayed during recovery; verified with SIGKILL mid-split. | Resolved | Full WAL logging for B+Tree splits, merges, and key updates
WAL / Durability | Idempotency & Checkpointing | PageLSN checked before redo; checkpoint does NOT truncate active log | Page LSN check; fuzzy checkpointing flushes dirty pages in background | Resolved (Sprint 2): Off-heap DirectByteBuffer/MemorySegment buffer pool; background dirty page flusher thread flushes unpinned dirty pages under page read lock. | Resolved | Background fuzzy checkpointing + Page LSN validation
Indexes | B-Tree Concurrency & Latching | Lehman-Yao B-link tree with high keys and concurrent latch crabbing | Index root latch + page latch crabbing with optimistic search | Synchronized wrapper; no fine-grained latch crabbing (races on split) | CRITICAL | Multi-page latch crabbing (ReadWriteLock) during traversal/split
Indexes | Free-Space Reuse in Indexes | Orphaned index pages tracked in FSM and recycled on future splits | B+tree page merge reclaims page to space allocation list | Page merge orphans page permanently; file never reclaims space | Medium | Index page freelist for zero-waste page recycling
Indexes | Index Types Supported | B-Tree, Hash, GiST, GIN, BRIN, SP-GiST | B+Tree, Hash (Memory), R-Tree (Spatial), Full-Text | B+Tree, Hash, BRIN, Bitmap, GIN (text/array/json), GiST (intervals) | Medium | Excellent indexing breadth; harden concurrency & WAL
Query Engine | Execution Architecture | Volcano Iterator model (open, next, close) streaming single tuples | RowIterator model (open, Read, close) streaming rows one by one | Monolithic ExecutorEngine loading entire tables into List<Tuple> in RAM | CRITICAL | Volcano Iterator PhysicalOperator pipeline streaming rows
Query Engine | Cost-Based Optimizer (CBO) | Advanced CBO with statistics histograms, MCV, dynamic programming join order | Cost-based optimizer using table stats and hypergraph join planner | Simple scan cost (seq vs index); hardcoded merge join row threshold (>10k) | High | System-R dynamic programming join optimizer with histograms
Query Engine | Join Types & Capabilities | Nested Loop, Hash Join, Merge Join, Semi-Join, Anti-Join, Left/Right/Full Outer | Hash Join, Block Nested Loop, Index Nested Loop, Outer Joins | Hash Join (inner equality) and Merge Join; no outer joins; no join reorder | High | Outer joins (Left/Right/Full), Index Nested Loop, Semi-joins
SQL & Constraints | Constraint Enforcement | Enforced PRIMARY KEY, UNIQUE, FOREIGN KEY (CASCADE), CHECK, NOT NULL | Enforced PRIMARY KEY, UNIQUE, FOREIGN KEY (CASCADE), CHECK, NOT NULL | Resolved (Sprint 4): PRIMARY KEY & UNIQUE (SQLSTATE 23505), FOREIGN KEY referential integrity with ON DELETE/UPDATE CASCADE/SET NULL/RESTRICT (SQLSTATE 23503), NOT NULL (SQLSTATE 23502), and CHECK expressions (SQLSTATE 23514). | Resolved | Full constraint enforcement engine throwing standard SQLSTATEs
Network & Security | Wire Protocol Completeness | pgwire v3: Simple, Extended (Parse/Bind/Describe/Execute), CopyIn/CopyOut | MySQL client/server protocol (binary & text prepared statements) | pgwire v3 simple + extended query protocol + CopyIn/CopyOut | Medium | Binary parameter decoding (eliminate text interpolation)
Network & Security | Wire Encryption (TLS/SSL) | Native TLS 1.3 with ALPN, client cert auth, SCRAM channel binding | Native OpenSSL/yaSSL integration with client certs | StdWireServer declines SSL unconditionally; TlsSupport only in dead server | CRITICAL | Full SSLEngine TLS 1.3 integration in StdWireServer

## Java vs Rust Engine Strategy
LANGUAGE SELECTION STRATEGY: PURE JAVA 25 VS. RUST / HYBRID FOR STRATOSDB
Deep Technical Systems Evaluation: Garbage Collection, Memory Safety, Throughput & Development Velocity
Evaluation Category | Pure Java 25 (Current Path) | Rust (Alternative Path) | Hybrid Strategy (Java + Native Kernels) | Strategic Recommendation for StratosDB
Development Velocity & Existing Codebase | StratosDB already has ~38,000 lines of working, verified Java code across 12 modules. Velocity is extremely high. | Rewriting 38,000 lines into Rust requires 12-18 months of ground-up rebuild. Complete halt to new features. | Keep Java core engine; selectively introduce Rust/C for SIMD compression or crypto kernels. | STAY IN JAVA. Rebuilding in Rust is a classic second-system trap that will kill momentum.
Garbage Collection & Latency (P99) | Standard Java heap objects trigger GC pauses. Java 25 Generational ZGC reduces pauses to <1ms on terabyte heaps. | Deterministic memory deallocation via RAII. Zero GC pauses, rock-solid predictable P99/P99.9 latency. | Off-heap buffer pool in Java (DirectByteBuffer/MemorySegment) keeps 95% of data away from GC. | Use Java Off-Heap Memory (Panama FFM API) + Generational ZGC. Solves 99% of GC issues in Java.
Memory Layout & Cache Locality | 16-byte object headers + 8-byte pointers cause cache misses if row objects are inflated into heap. | Contiguous structs, zero-cost abstractions, perfect L1/L2 cache locality, no pointer chasing. | Keep tuples in contiguous byte pages in off-heap memory. Access columns via byte offsets, not Objects. | Adopt Slotted Page zero-copy accessors. Treat pages as raw byte buffers; do not instantiate Tuple objects.
Concurrency & Threading Model | Project Loom (Virtual Threads) allows 100,000+ concurrent network connections with zero thread pool overhead. | Async/await (Tokio) or OS threads. Highly efficient, but async Rust introduces colored functions and lifetime complexity. | Virtual Threads in StdWireServer provide world-class concurrency with synchronous, readable code. | Java Virtual Threads are an enormous competitive advantage over C/Rust process-per-client models.
Direct Hardware Access & Kernel I/O | Standard FileChannel lacks O_DIRECT (double buffering). Java 22+ Panama FFM can invoke Linux preadv2 with O_DIRECT. | Trivial access to O_DIRECT, io_uring, and SIMD instructions (AVX-512) via native crate ecosystem. | Call native io_uring or libc O_DIRECT via Foreign Linker API without tedious JNI glue. | Use Java Foreign Function & Memory (FFM) API for direct I/O when raw disk bandwidth is the bottleneck.
Real-World Proof of Concept | Apache Cassandra, H2 Database, Apache Derby, Neo4j, Trino/Presto, Apache Kafka, Apache Lucene. | TiKV, Neon (Postgres storage), DataFusion, SurrealDB, RisingWave, Qdrant. | RocksDB (C++) with Java JNI wrapper; Spark with native Tungsten engine. | Pure Java databases run mission-critical enterprise workloads globally at massive scale.
STRATEGIC VERDICT & ARCHITECTURAL DIRECTIVE
Verdict | BUILD IN PURE JAVA 25. DO NOT REWRITE IN RUST.
Why? | Java 25 has evolved into an enterprise systems language with Virtual Threads (Loom), Foreign Function & Memory (Panama), Vector API, and Generational ZGC. StratosDB has 38,000 lines of working, battle-tested code. A Rust rewrite would destroy this progress for zero immediate functional gain.
The Golden Rule | Keep all page caches and row buffers OFF-HEAP. Use streaming iterators. Let Virtual Threads handle network I/O. Tune with -XX:+UseZGC -XX:+ZGenerational.

## Production Checklist and KPIs
STRATOSDB PRODUCTION READINESS CHECKLIST & MEASURABLE KPIS
Strict Objective Verification Criteria for Enterprise Production Deployments
Category | Verification Requirement | Target Standard / Metric | Test Harness / Methodology | Status
ACID Durability | Crash Recovery under Heavy Write Load | Zero uncommitted rows visible; 100% committed rows restored exactly | Kill forked JVM process mid-batch with SIGKILL; restart and verify row counts | Passed (Week 1)
ACID Durability | B+Tree Structural Consistency across Crashes | No corrupted tree pointers, no orphan pages, all keys searchable | Inject SIGKILL during multi-level B+tree leaf split; verify via tree validation pass | Passed (Week 3)
Concurrency | Deadlock Detection & Resolution | Deadlock detected in <100ms; one transaction aborted with SQLSTATE 40P01 | LockManagerDeadlockTest with cyclic multi-threaded wait-for graph | Passed (Week 2)
Concurrency | B+Tree Multi-Threaded Stress Test | Zero race conditions or data loss under 64 concurrent writers and 128 readers | Concurrent 500,000 key insert/update/delete stress harness | Pending Month 4
Schema Integrity | Foreign Key Referential Integrity | Orphan child inserts blocked; cascading deletes cascade reliably | Multi-table relational integrity suite with deep 4-level cascading deletes | Passed
Schema Integrity | Primary Key & Unique Constraint Enforcement | Duplicate key insert throws SQLSTATE 23505; zero duplicate keys in index | Concurrent insertion race on identical primary key values | Passed
Memory & Performance | Heap Allocation during Sequential Scans | Zero OOM; memory usage bounded by work_mem (<64MB) on 10M row scan | Volcano streaming scan against 10M row table with 512MB max JVM heap | Pending Month 3
Memory & Performance | P99 Latency & GC Pause Time | P99 latency < 2.0ms; maximum STW GC pause < 1.0ms under 15,000 QPS | StratosBench / pgbench TPC-B workload with Generational ZGC logging enabled | Pending Month 6
Security & Auth | Wire Protocol TLS 1.3 Encryption | All socket bytes encrypted; psql sslmode=verify-full connects cleanly | Wireshark packet capture inspecting psql client handshake over port 6583 | Pending Month 5
Ecosystem | Hibernate ORM & Spring Boot Compatibility | Spring Data JPA PetClinic application runs all CRUD operations unmodified | Automated integration test running Spring Boot PetClinic against StratosDB | Pending Month 6
Ecosystem | Database GUI Tool Compatibility | DBeaver, DataGrip, and pgAdmin can browse tables, columns, indexes, and run SQL | Interactive GUI connection verification via emulated pg_catalog | Pending Month 2